

|  |  |
| --- | --- |
| Aristotle University of Thessaloniki (AUTH) Greece | Industrieanlagen Betriebsgesellschaft MBH (IABG) Germany |
| Gounaris N. – Kontos K. OE (HOMEOTECH) Greece | Centrum Badan Kosmicznych Polskiej Akademii Nauk (CBK PAN) Poland |
| Universitat Politecnica de Valencia (UPV) Spain | Fundacion Centro De Servicios Y Promocion FOrestral Y de su Industria De Castilla y Leon (CESEFOR) Spain |

|  |  |
| --- | --- |
| MN.03 | Minutes for 1st Project Meeting |
|  | |
| **MAIL**: Identifying Marginal Lands in Europe and strengthening their contribution potentialities in a CO2 sequestration strategy | |

|  |  |
| --- | --- |
| **Type** | Minutes |
| **Meeting** | 1st Project Meeting |
| **Place** | CESEFOR, Soria, Spain |
| **Date** | 22-23 October 2019 |

**Agenda**

**1st Project Meeting**

Organized by:

**CESEFOR**

**Day 1 (Tuesday, 22nd October 2019) – Technical session**

|  |  |
| --- | --- |
| 09:00 | **Welcome by Cesefor director and the project coordinator** |
| 09:15 | **T2.1 Literature review on ML definition** *(CESEFOR/IAGB)*   * Results * Discussion |
| 10:00 | **T.2.2 Collection of appropriate existing European/Global datasets** *(AUTH/HOMEOTECH)*   * Results * Discussion |
| 10:45 | **Coffee break** |
| 11:00 | **T.2.3 Methodology development of m/sm MLs detection** *(AUTH/CESEFOR)*   * Set out the task * Progress * Discussion |
| 11:45 | **T.2.5 Existing models (IPCC,…) customization, evaluation, validation considering local aspects** *(CESEFOR/HOMEOTECH)*   * Set out the tasks * Progress * Discussion |
| 12:30 | **T.5.2 Financial, social and technical aspects of the sustainable development of MLs** *(IAGB/AUTH)*   * Set out the task * Progress * Discussion |
| 13:15 | **Lunch** |
| 15:00 | **T.5.3 Potentialities of emerging stock exchange markets for carbon transactions and proposed policies** *(CESEFOR/HOMEOTECH)*   * Set out the task * Progress * Discussion |
| 15:45 | **WP7 Project management** *(AUTH)*   * Future steps and secondment planning * Discussion |
| 16:00 | **WP 6 Communication** *(CBK)*   * Deliverable 6.1 * Instructions * 2019 actions * Questions and answers |
| 16:45 | **Closing the day** |
| 19:30 | **City tour and all-together Dinner** |

**Day 2 (Wednesday, 23rd October, 2019) – Technical session / field trip**

|  |  |
| --- | --- |
| 09:00 | **2020 year planning. Coordination plan** *(AUTH)*   * Current situation * 2020 secondment plan. * Procedures, news, more * Next events (workshops and next meeting) |
| 10:30 | **WP2 Research** *(AUTH)*   * Work planning and future steps * Secondment planning * T2.6 (IABG) * T2.10 (UPV) * Discussion |
| **11:00** | **Coffee break** |
| 11:30 | **WP4 Pilot case studies** *(CESEFOR)*   * Work planning and future steps * Secondment planning * Discussion |
| 12:00 | **WP5 Technical and financial feasibility study** *(IAGB)*   * Work planning and future steps * Secondment planning * T5.4 (HOMEOTECH) * Discussion |
| 12:30 | **WP6 Dissemination and awareness** *(CBK)*   * Work planning and future steps * Discussion |
| 13:00 | **Lunch** |
| 14:00 | **Field trip**   * Visit to a marginal land in Soria * Ongoing restoration project |
| 18:30 | **Closing the day** |
| 20:00 | **Dinner** |

**Participants**

|  |  |  |
| --- | --- | --- |
| 1. Charalampos Georgiadis | AUTH |  |
| 1. Nikolaos Gounaris 2. Lampros Papalampros 3. Anna Argyroudi | HOMEOTECH |  |
| 1. Rodrigo Gomez 2. Francisco Gallego 3. Concha Redondo | CESEFOR |  |
| 1. Martin Lindner | IABG |  |
| 1. Luis Angel Ruiz Fernandez 2. Juan Pedro Carbonell Rivera | UPV |  |
| 1. Edyta Wozniak | CBK PAN |  |

# Work package 1

WP1. Ethics Requirements

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **What** | **Who** | **When** |
|  | D1.1 UPV and AUTH’s MOOC and Virtual classroom platforms will be used for the implementation of the platform. WebGIS usage will not require registration and it will be open to any potential user. Data for the open research data pilot will be uploaded to the zenodo platform |  |  |

# Work package 2

WP2. Research

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **What** | **Who** | **When** |
|  | T2.1 Provide a general definition of marginal lands and a more concise object-oriented definition tailored to the MAIL aim goals | CESEFOR | 30-11-2019 |
|  | T2.2 Investigate the creation of a de-population indicator | HOMEOTECH | 30-11-2019 |
|  | T2.3  Probability index for marginal lands  ML 1 Hectare  GIS Specs and design  Exclusions of non-land use layers 1st step  Forestry variables  Soil variables  Time series for Corine land change layers  Social economic data and changes (database extension for pilot cases) | CESEFOR | 31-10-2018 |
|  | Ask the PO if we can move UPV’s T2.3 6-month secondment to IABG starting on M19 to M15 and split it between Tasks 2.3 (3 months) and 2.6 (3 months). The above action will help the better and more efficient implementation of the project. |  |  |
|  | T2.4 Provide the T2.4 Planning document | UPV | 15-11-2019 |
|  | T2.5 provide a draft of the work (upload in the consortium members space) as soon as the 1st secondment ends | HOMEOTECH | 31-12-2019 |
|  | T2.6 Ask the PO if we can implement the following modifications with respect to IABG’s secondments.  IABG has currently the following secondements in T2.6  IABG to CBK M14-M18 (5 months)  IABG to AUTH M16-M17 (2 months)  The modified secondments will be  IABG to CBK M16-M18 (3 months)  IABG to AUTH M16-M18 (3 months)  We also want to move the remaining month to T2.7 and extent the one month secondment of IABG to AUTH to 2 months.  The initial secondment was for M26, the modified will be M25-M26.  The above mentioned modifications will help to the better and more efficient implementation of the project. |  |  |
|  | Since UPV and AUTH infrastructure includes platforms for MOOCs and Virtual classrooms it would not be efficient and productive to develop a new platform exclusively for the project.  Currently the following secondments are planned for T2.10:  HOMEOTECH to UPV M6-M7 (2 months)  HOMEOTECH to UPV M25-M28 (4months)  We want to move the 2 month secondment to M29-M30 (Final stage of the implementation of the developed service to the project website)  The 4 month secondment allocated to the Task 2.10 will be used more efficiently and productive if they are reallocated to Task 2.9 for the development of the WebGIS (4 months), as a result we want to modify this secondment as follows:  HOMEOTECH to CESEFOR M24-M27 (4 months) T2.9 |  |  |

# Work package 3

WP3. Training on Remote Sensing and state of the art practices

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **What** | **Who** | **When** |
|  | WP 3 planning document | UPV | 30-11-2019 |
|  | T3.1 Planning document | UPV | 30-11-2019 |
|  | T3.2 Planning Document | UPV | 30-11-2019 |

# Work package 4

WP4. Pilot case studies

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **What** | **Who** | **When** |
|  | Provide additional pilot areas (Compatible pilot sites sizes, alternatively using additional pilot sites) | All | 31-12-2019 |
|  | T4.1 Using RS for MLs detection/monitoring |  |  |

# Work package 5

WP5. Technical and financial feasibility study

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **What** | **Who** | **When** |
|  | Task 5.2 the use of public fund will also be examined in the sustainability assessment of using marginal lands as carbon sinks |  |  |
|  | Task 5.3, The draft of version of the document draft produced by the first secondment will be uploaded to the members space | CESEFOR | 28-10-2019 |

# Work package 6

WP6. Dissemination and awareness

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **What** | **Who** | **When** |
|  | Workshops Organization Plan | All | 15-1-2020 |
|  | Preparation of workshops Agenda plan | CBK | 31-12-2019 |
|  | Leaflet Preparation | CBK | 31-12-2019 |
|  | 2nd Newsletter | CBK | 31-12-2019 |
|  | Finished Public deliverables should be uploaded to the website, for nonpublic deliverables publish an executive summary | HOMEOTECH |  |

# Work Package 7

WP7. Project Management

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **What** | **Who** | **When** |
|  | WP leaders provide input for the 1st Progress report | WPL | 15-12-2019 |
|  | Mid Term meeting finalization | AUTH, CBK | 15-11-2019 |
|  | Secondments planning Finalization (1st Semester 2020) | All | 15-11-2019 |
|  | Secondments planning Finalization (2nd Semester 2020) | All | 15-1-2020 |

# General

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **What** | **Who** | **When** |
|  |  |  |  |

# Annex I Participants list



