

|  |  |
| --- | --- |
| Aristotle University of Thessaloniki (AUTH) Greece | Industrieanlagen Betriebsgesellschaft MBH (IABG) Germany |
| Gounaris N. – Kontos K. OE (HOMEOTECH) Greece | Centrum Badan Kosmicznych Polskiej Akademii Nauk (CBK PAN) Poland  |
| Universitat Politecnica de Valencia (UPV) Spain | Fundacion Centro De Servicios Y Promocion FOrestral Y de su Industria De Castilla y Leon (CESEFOR) Spain |

|  |  |
| --- | --- |
| MN.02 | Minutes for 1st Teleconference Technical Meeting  |
|  |
| **MAIL**: Identifying Marginal Lands in Europe and strengthening their contribution potentialities in a CO2 sequestration strategy |

|  |  |
| --- | --- |
| **Type** | Minutes |
| **Meeting** | 1st Teleconference Technical Meeting |
| **Place** | Teleconference |
| **Date** | 12 July 2019 |

**Agenda**

**1st Teleconference Technical Meeting**

Organized by:

**The Aristotle University**

|  |  |
| --- | --- |
|  | **Task 2.1 Literature review on marginal lands definition** |
|  | **Current Status 5 min presentation (CESEFOR)** |
|  | Discussion |
|  | Action Plan/Way Forward |
|  | **Task 2.2 Collection of appropriate existing European/Global Datasets** |
|  | Current Status 5 min presentation (HOMEOTECH) |
|  | Discussion |
|  | Action Plan/Way Forward |
|  | **Task 2.3 Methodology development of m/sm MLs detection** |
|  | Planning 5 min presentation (AUTH) |
|  | Discussion |
|  | Action Plan/Way Forward |
|  | **Task 2.5 Existing models (IPCC, etc.) customization - evaluation - validation, considering local aspects** |
|  | Planning 5 min presentation (CESEFOR) |
|  | Discussion |
|  | Action Plan/Way Forward |
|  | **Task 5.2 Financial social and technical aspects of the sustainable development of MLs** |
|  | Planning 5 min presentation (IABG) |
|  | Discussion |
|  | Action Plan/Way Forward |
|  | **Task 5.3 Potentialities of emerging stock exchange markets for carbon transactions and proposed policies** |
|  | Planning 5 min presentation (CESEFOR) |
|  | Discussion |
|  | Action Plan/Way Forward |
|  | **WP 6 Dissemination and awareness** |
|  | Dissemination and Communication actions (CBK PAN) |
|  | Discussion |
|  | Action Plan/Way Forward |
|  | **Meeting minutes Finalization** |

**Participants**

|  |  |  |
| --- | --- | --- |
| 1. Charalampos Georgiadis
2. Vasileios Tsioukas
3. Maria Tassopoulou
4. Natalia Verde
 | AUTH |  |
| 1. Nikolaos Gounaris
2. Lampros Papalampros
 | HOMEOTECH |  |
| 1. Rodrigo Gomez
2. Francisco Gallego
3. Alfonso Abad
 | CESEFOR |  |
| 1. Martin Lindner
2. Elke Kraetzschmar
3. Bettina Felten
 | IABG |  |
| 1. Edyta Wozniak
2. Michal Krupinski
 | CBK PAN |  |

# Work package 1

WP1. Ethics Requirements

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **What** | **Who** | **When** |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

# Work package 2

WP2. Research

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **What** | **Who** | **When** |
|  | Task 2.2 CBK sends information for new land cover dataset based in sentinel dataIABG send information about the European High-resolution layer  | IABG, CBK PAN | 31/07/2019 |
|  | Task 2.1 Definition of parameters that will help Exclude areas that cannot be used for carbon stocking  | CESEFOR | 30/09/2019 |
|  | The GIS will be developed using the EU projection according to the INSPIRE directive  |  |  |
|  | GIS development will be implemented using QGIS |  |  |
|  | Inform the consortium for the possibility that the secondees can use ArcGIS in the premises of IABG | IABG | 31/07/2019 |

# Work package 3

WP3. Training on Remote Sensing and state of the art practices

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **What** | **Who** | **When** |
|  |  |  |  |

# Work package 4

WP4. Pilot case studies

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **What** | **Who** | **When** |
|  | Definition of pilot sites  | All | 27/09/2019 |

# Work package 5

WP5. Technical and financial feasibility study

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **What** | **Who** | **When** |
|  |  |  |  |
|  |  |  |  |

# Work package 6

WP6. Dissemination and awareness

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **What** | **Who** | **When** |
|  | 1st MAIL Newsletter | CBK PAN | 26/07/2019 |
|  | Assignment of persons responsible for social media dissemination  | All | 31/07/2019 |
|  | November 2019 Workshop preparation | All | 31/08/2019 |
|  | Preparation of the Annual leaflet report | CBK PAN | 30/09/2019 |
|  | Everybody sends their researchgate profile to CBK PAN | All | 31/07/2019 |
|  | Everybody sends consent about sharing photos and video | All | 09/08/2019 |
|  | Add social media links to MAIL website | HOMEOTECH | 31/07/2019 |

# Work Package 7

WP7. Project Management

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **What** | **Who** | **When** |
|  | 1st Project meeting in Soria organization  | AUTH, CESEFOR | 31/07/2019 |

# General

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **What** | **Who** | **When** |
|  |  |  |  |